## Slide 1: Grant Sources & Strategies
Rebecca Hartzler & Christopher Tassava
PKAL/QuIRK Workshop
October 9, 2010
Carleton College

## Slide 2: Chronological Structure
Planning and Applying
Grant Writing Phase
Project Phase
Post-Grant/Continuation
QuIRK Case Study

## Slide 3: Planning & Applying Phase
Identifying likely funders and working with program officers
Establishing internal and external partners
Choosing a focus/scope for the project
Creating a detailed project plan
Projecting a confident writing voice
Formatting for quick reading

## Slide 4: Identifying likely funders and working with program officers
FIPSE, National Science Foundation, appropriations, private & college foundations, faculty development funds (Foundation Directory Online)
Three key actions
  Read the RFP
    Read the RFP
      Read the RFP
Talk to agency program officers

## Slide 5: Establishing internal and external partners
Internal Partners - determine who your project will affect and ask for their input and commitment
  Administration
  Faculty
  Student services
  Assessment & Institutional Research
  Marketing
  Students
  Staff

## Slide 6: Establishing internal and external partners
External Partners
  Consultants
  Evaluators

## Slide 7: Choosing a focus/scope for the project
Start small and build on your strengths
  QuIRK
  MAC3

## Slide 8: Create a Detailed Project Plan
Do your homework – what’s been done before? Abide by a culture of evidence
Use consultants for advice
Get commitment from everyone involved
Be as specific as possible

## Slide 9: Projecting Confidence
Provide a sketch of the project early on
Example from EdCC’s S-STEM grant:
  “The need for the Scholarship project is great.”
  “The management team is committed and qualified. . . .”
  “The management plan is well-conceived . .”
  “The innovative adaptation of mentoring and internship programs . . .”

## Slide 10: Formatting for Quick Reading
Use of tables
Use of headings
Use of pictures
Long vs. short

## Slide 11: Project Phase
Maintaining internal and external partnerships
Growing faculty and administrative committment
Establishing a balanced leadership team
Active project management
Adapting to new circumstances
Tracking project budget
Making significant curricular changes
Project evaluation
Dissemination
Meeting funder expectations

## Slide 12: Maintaining internal and external partnerships
Partnerships are typically the core of the project
  Internally, faculty across departments
  Externally, partner institutions

## Slide 13: Establishing a balanced leadership team
Delusionally optimistic + grounded = great team
Power moves between team members
Open disagreement is encouraged
Common commitment around a “Cause”
Common work methods

## Slide 14: Growing faculty and administrative commitment – esp. interdisciplinary
Faculty need to be given room and resources to create
Administrators need to back the project
Administrators care about
  Indirect funding
  Accreditation
  Student retention
  College image

## Slide 15: Active Project Management
Get a project manager
  Sends out reminder emails, tracks the budget, organizes workshops, creates workshop packets, answers questions from participants, helps with reimbursement forms and travel plans, etc.
Hire assistants
  Stuff folders, plan and pick-up food, prints out name tags, etc.

## Slide 16: Adapting to New Circumstances
Work with your program officer to learn what changes are possible
Changes should be driven by results
Sometimes a change in scope is appropriate

## Slide 17: Tracking the Budget
Meet with the budget office initially to review the budget
Begin tracking immediately
Keep records on every expenditure
Reconcile early and often

## Slide 18: Making Significant Curricular Change
Faculty need to have time set aside to work out the issues and build curriculum
Faculty need to create authentic relationships
Create an atmosphere of trust
Provide resources
Provide feedback
Build assessment into the project

## Slide 19: Project Evaluation
Oriented toward outcomes
The instruments are out there
Employ a professional evaluator (internal or external)

## Slide 20: Dissemination
Join the QL community
  National Numeracy Network
    Numeracy Journal
  SIGMAA QL
    January and August meetings
  MQED
    Publish curriculum
  QuIRK – especially with external partners
  Discipline specific teaching journals

## Slide 21: Meeting funder expectations
Annual reports
  Understand format s ahead of time
Monitor budgets
  Changing budgets

## Slide 22: Post-Grant Phase
Identifying sources of continuing funding
Writing new proposals based upon relationships, achievements and future progress

## Slide 23: In Conclusion
Questions? Or Comments?
Christopher Tassava, ctassava@carleton.edu
Rebecca Hartzler, rebecca.hartzler@edcc.edu